## Gantt Chart
ID | Task Name | Start Date | End Date | Duration | Resources | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Apr 2025 | May 2025 | Jun 2025 | Jul 2025 | Aug 2025 | Sep 2025 | Oct 2025 | Nov 2025 | Dec 2025 | Jan 2026 | Feb 2026 | Mar 2026 | Apr 2026 | May 2026 | Jun 2026 | Jul 2026
1 | PHASE 1: PRE-WORKSHOP | 01/12/2024 | 31/03/2026 | 486
1.1 | Initial Setup | 01/12/2024 | 28/02/2025 | 90
1.1.1 | CCG Application Submission | 01/12/2024 | 31/12/2024 | 31 | FHGR Lead
1.1.2 | Committee Formation | 01/12/2024 | 28/02/2025 | 90 | FHGR/AUS
1.1.3 | Website Development | 01/12/2024 | 28/02/2025 | 90 | Technical Team
M1 | MILESTONE: CCG Approval | 28/02/2025 | 28/02/2025 | 1 |  |  |  | ◆
1.2 | Call for Papers & Marketing | 01/02/2025 | 31/08/2025 | 212
1.2.1 | Call for Papers Issuance | 01/02/2025 | 31/03/2025 | 59 | Committee
1.2.2 | Speaker Invitations | 01/02/2025 | 31/08/2025 | 212 | FHGR/AUS
1.2.3 | Marketing Campaigns | 01/03/2025 | 31/08/2025 | 184 | Marketing Team
1.2.4 | Paper Submissions | 01/03/2025 | 31/08/2025 | 184 | Researchers
1.2.5 | Registration Opening | 01/03/2025 | 31/08/2025 | 184 | AUS Team
1.3 | Review & Program Development | 01/09/2025 | 31/10/2025 | 61
1.3.1 | Paper Review Process | 01/09/2025 | 31/10/2025 | 61 | Review Committee
1.3.2 | Acceptance Notifications | 01/09/2025 | 31/10/2025 | 61 | Committee
1.3.3 | Program Finalization | 01/09/2025 | 31/10/2025 | 61 | FHGR/AUS
1.4 | Speaker & Venue Confirmations | 01/11/2025 | 31/01/2026 | 92
1.4.1 | Speaker Confirmations | 01/11/2025 | 31/01/2026 | 92 | FHGR/AUS
1.4.2 | Venue Planning | 01/11/2025 | 31/01/2026 | 92 | AUS Team
1.4.3 | Technical Setup Planning | 01/11/2025 | 31/01/2026 | 92 | Technical Team
1.5 | Final Preparations | 01/02/2026 | 31/03/2026 | 59
1.5.1 | Materials Preparation | 01/02/2026 | 31/03/2026 | 59 | Committee
1.5.2 | Bilateral Agreement Drafting | 01/02/2026 | 31/03/2026 | 59 | FHGR/AUS Legal
1.5.3 | Final Logistics | 01/02/2026 | 31/03/2026 | 59 | AUS Team
M2 | MILESTONE: All Speakers Confirmed | 31/03/2026 | 31/03/2026 | 1 | [16 empty] | ◆
2 | PHASE 2: WORKSHOP | 01/04/2026 | 23/04/2026 | 23
2.1 | Final Workshop Preparations | 01/04/2026 | 14/04/2026 | 14
2.1.1 | Final Preparations | 01/04/2026 | 14/04/2026 | 14 | All Teams
2.1.2 | Technical Testing | 01/04/2026 | 14/04/2026 | 14 | Technical Team
2.1.3 | Registration Push | 01/04/2026 | 14/04/2026 | 14 | Marketing Team
M3 | MILESTONE: 80+ Participants Registered | 15/04/2026 | 15/04/2026 | 1 | [17 empty] | ◆
2.2 | Workshop Execution | 21/04/2026 | 23/04/2026 | 3
2.2.1 | Day 1: Research Frontiers | 21/04/2026 | 21/04/2026 | 1 | All Participants
2.2.2 | Day 2: Industry Applications | 22/04/2026 | 22/04/2026 | 1 | All Participants
2.2.3 | Day 3: Training & Working Groups | 23/04/2026 | 23/04/2026 | 1 | All Participants
M4 | MILESTONE: Workshop Delivered | 23/04/2026 | 23/04/2026 | 1 | [17 empty] | ◆
M5 | MILESTONE: 15-20 Papers Presented | 23/04/2026 | 23/04/2026 | 1 | [17 empty] | ◆
2.2.4 | AUS-FHGR Agreement Signing | 23/04/2026 | 23/04/2026 | 1 | Leadership
M6 | MILESTONE: Bilateral Agreement Signed | 23/04/2026 | 23/04/2026 | 1 | [17 empty] | ◆
3 | PHASE 3: POST-WORKSHOP | 01/05/2026 | 31/07/2026 | 92
3.1 | Immediate Follow-up | 01/05/2026 | 31/05/2026 | 31
3.1.1 | Feedback Collection | 01/05/2026 | 31/05/2026 | 31 | Committee
3.1.2 | Impact Assessment | 01/05/2026 | 31/05/2026 | 31 | FHGR/AUS
3.1.3 | Proceedings Compilation | 01/05/2026 | 31/05/2026 | 31 | Editorial Team
3.2 | Reporting & Publication | 01/06/2026 | 30/06/2026 | 30
3.2.1 | CCG Reporting | 01/06/2026 | 30/06/2026 | 30 | FHGR Lead
3.2.2 | Proceedings Publication | 01/06/2026 | 30/06/2026 | 30 | Editorial Team
M7 | MILESTONE: Proceedings Published | 30/06/2026 | 30/06/2026 | 1 | [19 empty] | ◆
3.2.3 | Media Documentation | 01/06/2026 | 30/06/2026 | 30 | Marketing Team
3.3 | Sustainability Initiatives | 01/07/2026 | 31/07/2026 | 31
3.3.1 | Collaboration Platform Launch | 01/07/2026 | 31/07/2026 | 31 | Technical Team
3.3.2 | Working Group Activation | 01/07/2026 | 31/07/2026 | 31 | Working Groups
3.3.3 | Proposal Initiation | 01/07/2026 | 31/07/2026 | 31 | FHGR/AUS
M8 | MILESTONE: Report to CCG Submitted | 31/07/2026 | 31/07/2026 | 1 | [20 empty] | ◆

## Resource Summary
Resource | Total Hours | Contribution (CHF)
FHGR Lead | 32 hours | CHF 2,500 (in-kind)
AUS Lead | 50 hours | CHF 10,500 (in-kind)
AUS Cash | - | CHF 600
CCG Funding | - | CHF 5,000
Total Budget | 82 hours | CHF 18,000
Co-funding |  | CHF 13,000 (72%)

## Milestones
Milestone | Date | Description
CCG Approval | February 2025 | Funding secured to proceed
All Speakers Confirmed | March 2026 | Speaker lineup finalized
80+ Participants Registered | April 15, 2026 | Registration target achieved
Workshop Delivered | April 21-23, 2026 | 3-day workshop executed
15-20 Papers Presented | April 21-23, 2026 | Academic content delivered
Bilateral Agreement Signed | April 23, 2026 | AUS-FHGR collaboration formalized
Proceedings Published | June 2026 | Workshop outputs disseminated
Report to CCG Submitted | July 2026 | Final reporting completed