## Gantt Chart
ID | Task Name | Start Date | End Date | Duration | Resources | Dec 2025 | Jan 2026 | Feb 2026 | Mar 2026 | Apr 2026 | May 2026 | Jun 2026 | Jul 2026
1 | PHASE 1: PRE-WORKSHOP | 01/12/2025 | 31/03/2026 | 121
1.1 | Initial Setup & Call for Papers | 01/12/2025 | 31/12/2025 | 31
1.1.1 | Committee Formation | 01/12/2025 | 15/12/2025 | 15 | FHGR/AUS
1.1.2 | Website Development | 01/12/2025 | 31/12/2025 | 31 | Technical Team
1.1.3 | Call for Papers Issuance | 15/12/2025 | 31/12/2025 | 17 | Committee
1.2 | Marketing & Paper Submissions | 01/01/2026 | 31/01/2026 | 31
1.2.1 | Marketing Campaigns Launch | 01/01/2026 | 31/01/2026 | 31 | Marketing Team
1.2.2 | Speaker Invitations | 01/01/2026 | 31/01/2026 | 31 | FHGR/AUS
1.2.3 | Paper Submission Period | 01/01/2026 | 31/01/2026 | 31 | Researchers
1.2.4 | Registration System Setup | 01/01/2026 | 15/01/2026 | 15 | AUS Team
1.2.5 | Registration Opening | 15/01/2026 | 31/01/2026 | 17 | AUS Team
1.3 | Review & Program Development | 01/02/2026 | 28/02/2026 | 28
1.3.1 | Paper Review Process | 01/02/2026 | 15/02/2026 | 15 | Review Committee
1.3.2 | Acceptance Notifications | 15/02/2026 | 20/02/2026 | 6 | Committee
1.3.3 | Program Finalization | 20/02/2026 | 28/02/2026 | 9 | FHGR/AUS
1.3.4 | Venue Planning & Setup | 01/02/2026 | 28/02/2026 | 28 | AUS Team
1.3.5 | Technical Infrastructure Planning | 01/02/2026 | 28/02/2026 | 28 | Technical Team
1.4 | Final Preparations | 01/03/2026 | 31/03/2026 | 31
1.4.1 | Speaker Confirmations | 01/03/2026 | 15/03/2026 | 15 | FHGR/AUS
1.4.2 | Materials Preparation | 01/03/2026 | 31/03/2026 | 31 | Committee
1.4.3 | Bilateral Agreement Drafting | 01/03/2026 | 31/03/2026 | 31 | FHGR/AUS Legal
1.4.4 | Registration Drive | 01/03/2026 | 31/03/2026 | 31 | Marketing Team
1.4.5 | Logistics Finalization | 15/03/2026 | 31/03/2026 | 17 | AUS Team
M1 | MILESTONE: All Speakers Confirmed | 15/03/2026 | 15/03/2026 | 1 |  |  |  |  | ◆
2 | PHASE 2: WORKSHOP | 01/04/2026 | 23/04/2026 | 23
2.1 | Final Workshop Preparations | 01/04/2026 | 14/04/2026 | 14
2.1.1 | Final Arrangements | 01/04/2026 | 14/04/2026 | 14 | All Teams
2.1.2 | Technical Testing | 01/04/2026 | 14/04/2026 | 14 | Technical Team
2.1.3 | Final Registration Push | 01/04/2026 | 14/04/2026 | 14 | Marketing Team
M2 | MILESTONE: 80+ Participants Registered | 15/04/2026 | 15/04/2026 | 1 | [5 empty] | ◆
2.2 | Workshop Execution | 21/04/2026 | 23/04/2026 | 3
2.2.1 | Day 1: Research Frontiers | 21/04/2026 | 21/04/2026 | 1 | All Participants
2.2.2 | Day 2: Industry Applications | 22/04/2026 | 22/04/2026 | 1 | All Participants
2.2.3 | Day 3: Training & Working Groups | 23/04/2026 | 23/04/2026 | 1 | All Participants
M3 | MILESTONE: Workshop Delivered | 23/04/2026 | 23/04/2026 | 1 | [5 empty] | ◆
M4 | MILESTONE: 15-20 Papers Presented | 23/04/2026 | 23/04/2026 | 1 | [5 empty] | ◆
2.2.4 | AUS-FHGR Agreement Signing | 23/04/2026 | 23/04/2026 | 1 | Leadership
M5 | MILESTONE: Bilateral Agreement Signed | 23/04/2026 | 23/04/2026 | 1 | [5 empty] | ◆
3 | PHASE 3: POST-WORKSHOP | 01/05/2026 | 31/07/2026 | 92
3.1 | Immediate Follow-up | 01/05/2026 | 31/05/2026 | 31
3.1.1 | Feedback Collection | 01/05/2026 | 31/05/2026 | 31 | Committee
3.1.2 | Impact Assessment | 01/05/2026 | 31/05/2026 | 31 | FHGR/AUS
3.1.3 | Proceedings Compilation | 01/05/2026 | 31/05/2026 | 31 | Editorial Team
3.2 | Reporting & Publication | 01/06/2026 | 30/06/2026 | 30
3.2.1 | CCG Reporting | 01/06/2026 | 30/06/2026 | 30 | FHGR Lead
3.2.2 | Proceedings Publication | 01/06/2026 | 30/06/2026 | 30 | Editorial Team
M6 | MILESTONE: Proceedings Published | 30/06/2026 | 30/06/2026 | 1 | [7 empty] | ◆
3.2.3 | Media Documentation | 01/06/2026 | 30/06/2026 | 30 | Marketing Team
3.3 | Sustainability Initiatives | 01/07/2026 | 31/07/2026 | 31
3.3.1 | Collaboration Platform Launch | 01/07/2026 | 31/07/2026 | 31 | Technical Team
3.3.2 | Working Group Activation | 01/07/2026 | 31/07/2026 | 31 | Working Groups
3.3.3 | Joint Proposal Initiation | 01/07/2026 | 31/07/2026 | 31 | FHGR/AUS
M7 | MILESTONE: Report to CCG Submitted | 31/07/2026 | 31/07/2026 | 1 | [8 empty] | ◆

## Resource Summary
Resource | Total Hours | Contribution (CHF)
FHGR Lead | 32 hours | CHF 2,500 (in-kind)
AUS Lead | 50 hours | CHF 10,500 (in-kind)
AUS Cash | - | CHF 600
CCG Funding | - | CHF 5,000
Total Budget | 82 hours | CHF 18,000
Co-funding |  | CHF 13,000 (72%)

## Milestones
Milestone | Date | Description
All Speakers Confirmed | March 15, 2026 | Speaker lineup finalized
80+ Participants Registered | April 15, 2026 | Registration target achieved
Workshop Delivered | April 21-23, 2026 | 3-day workshop executed
15-20 Papers Presented | April 21-23, 2026 | Academic content delivered
Bilateral Agreement Signed | April 23, 2026 | AUS-FHGR collaboration formalized
Proceedings Published | June 30, 2026 | Workshop outputs disseminated
Report to CCG Submitted | July 31, 2026 | Final reporting completed

## Timeline Summary
Phase | Duration | Key Activities
Pre-Workshop | Dec 2025 - Mar 2026 (4 months) | Committee formation, CFP, marketing, reviews, preparations
Workshop | April 21-23, 2026 (3 days) | Research presentations, industry sessions, training, agreement signing
Post-Workshop | May - July 2026 (3 months) | Feedback, proceedings, reporting, sustainability initiatives
Total Duration | 8 months | Compressed timeline from December 2025 to July 2026