## Sheet1
Task | Start | End | Duration | Category | Responsible | Critical
Call for Papers Draft | 2025-01-15 | 2025-02-04 | 20 | Academic | Both | FALSE
Call for Papers Launch | 2025-02-15 | 2025-02-25 | 10 | Academic | FHGR | TRUE
Paper Submission Period | 2025-03-01 | 2025-08-28 | 180 | Academic | Authors | FALSE
Paper Review Process | 2025-09-01 | 2025-10-01 | 30 | Academic | Committee | TRUE
Paper Notifications | 2025-10-01 | 2025-10-11 | 10 | Academic | Chan | FALSE
Final Program Development | 2025-10-15 | 2025-11-29 | 45 | Academic | Both | TRUE
Proceedings Publication | 2026-05-01 | 2026-06-30 | 60 | Academic | Both | FALSE
CCG Application Submission | 2024-12-01 | 2024-12-16 | 15 | Administrative | Osterrieder/Chan | FALSE
CCG Review Period | 2024-12-15 | 2025-02-13 | 60 | Administrative | Leading House | TRUE
Committee Formation | 2024-12-20 | 2025-01-19 | 30 | Administrative | Both | FALSE
Workshop Execution | 2026-04-21 | 2026-04-24 | 3 | Administrative | All | TRUE
Network Activation | 2026-05-15 | 2026-07-14 | 60 | Administrative | Network Committee | FALSE
Final Reporting | 2026-06-01 | 2026-07-01 | 30 | Administrative | Osterrieder | FALSE
Venue Arrangements | 2025-02-01 | 2025-04-02 | 60 | Logistics | Chan/AUS | FALSE
Catering Planning | 2026-01-15 | 2026-04-15 | 90 | Logistics | AUS | FALSE
Materials Preparation | 2026-02-01 | 2026-04-17 | 75 | Logistics | Both | FALSE
Technical Setup | 2026-03-01 | 2026-04-15 | 45 | Logistics | Technical Team | TRUE
Final Preparations | 2026-04-01 | 2026-04-21 | 20 | Logistics | All Teams | TRUE
Website Development | 2025-01-10 | 2025-02-19 | 40 | Marketing/Outreach | Both | FALSE
Speaker Invitations | 2025-02-15 | 2026-02-15 | 365 | Marketing/Outreach | Osterrieder | TRUE
Website Launch | 2025-02-20 | 2025-02-25 | 5 | Marketing/Outreach | FHGR | FALSE
Marketing Campaign | 2025-03-01 | 2026-03-26 | 390 | Marketing/Outreach | Both | FALSE
Registration Opens | 2025-03-15 | 2026-03-20 | 370 | Marketing/Outreach | AUS | FALSE
Registration Drive | 2026-01-01 | 2026-04-16 | 105 | Marketing/Outreach | Both | TRUE